## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Image processing using OpenCV | MUST HAVE | Opencv , Pandas , matplotlib,imageAI | Prashant Singh | 3- Completed
S2 | S2 | US-002 | Object detection using tiny yolo | MUST HAVE | tiny-yolov3.pt model , torchvision torchaudio | Prashant Singh | 3- Completed
S3 | S3 | US-003 | Object Tracking ( DNN module ) | MUST HAVE | yolov4.cfg, yolov4.weights ,coco.names.txt | Prashant Singh | 3- Completed
S4 | S4 | US-004 | Dense optical flow | MUST HAVE | matplotlib , opencv | Prashant Singh | 3- Completed
S5 | S5 | US-005 | Sparse option flow | MUST HAVE | numpy , opencv | Prashant Singh | 3- Completed
S6 | S6 | US-006 | Image processing using OpenCV U.I. Implementation | MUST HAVE | Opencv , Pandas , matplotlib,imageAI , gradio | Prashant Singh | 3- Completed
S7 | S7 | US-007 | Object detection using tiny yolo U.I. Implementation | MUST HAVE | tiny-yolov3.pt model , torchvision torchaudio , gradio | Prashant Singh | 3- Completed
S8 | S8 | US-008 | Object Tracking ( DNN module ) U.I. Implementation | MUST HAVE | yolov4.cfg, yolov4.weights ,coco.names.txt , gradio | Prashant Singh | 3- Completed
Note on F1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 11 | 7.2 | 0.6 | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | TID-01 | Image processing using OpenCV | 2024-11-04 | 2024-11-06 | B.Varshitha Sri | Coding | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | TID-02 | Object detection using tiny yolo | 2024-11-07 | 2024-11-08 | B.Varshitha Sri | Coding | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | TID-03 | Object Tracking ( DNN module ) | 2024-11-11 | 2024-11-11 | B.Varshitha Sri | Coding | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | TID-04 | Dense optical flow | 2024-11-12 | 2024-11-15 | B.Varshitha Sri | Coding | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | TID-05 | Sparse option flow | 2024-11-16 | 2024-11-22 | B.Varshitha Sri | Coding | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | TID-06 | Image processing using OpenCV U.I. Implementation | 2024-11-23 | 2024-11-29 | B.Varshitha Sri | Build | 3- Completed | 2 | 1 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | TID-07 | Object detection using tiny yolo U.I. Implementation | 2024-12-02 | 2024-12-06 | B.Varshitha Sri | Build | 3- Completed | 2 | 1 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | TID-08 | Object Tracking ( DNN module ) U.I. Implementation | 2024-12-09 | 2024-12-13 | B.Varshitha Sri | Build | 3- Completed | 2 | 0.2 | 0.2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is the total task estimated in hours for all the user stories
Note on J3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 1 work
Note on K3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 2 work
Note on L3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 3 work
Note on M3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 4 work
Note on N3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 5 work
Note on O3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 6 work
Note on P3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 7 work
Note on Q3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 8 work
Note on R3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 9 work
Note on S3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 10 work
Note on T3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 11 work
Note on U3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 12 work
Note on V3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 13 work
Note on W3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Asked for notes on AI and tools | Conducted a detailed discussion with mentors and team
Sprint 1 | Day 4 | Query on Opencv and tensorflow topic | Conducted a team session and reviewed the project requirements with explaination
Sprint 2 | Day 6 | Agile template confusion | Conducted a meeting where all doubts were clarified by the mentor.
Sprint 2 | Day 7 | Confusion on Object Detection | Conducted additional research and consulted about the code.
Sprint 2 | Day 9 | Query on Object Tracking ( DNN module ) modules to be used | Created a code to explain the use of modules on the tracking code.
Sprint 3 | Day 12 | Query on Implementation of U.I | Mentor explained on how to create U.I & granted to use any resource
Sprint 4 | Day 16 | U.I model is Created | Conducted a team session and reviewed the project U.I Implementation with explaination
Sprint 5 | Day 23 | Query on some mistakes or changes | Provided solution about the issue and explained the process to solve it

## Retrospection
Overcomplicating solutions instead of keeping them simple. | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2024-11-04 | 2024-11-06 | B.Varshitha Sri | Exploring hands-on project to apply programming skills | Ignoring the importance of proper code documentation | Participating in discussions and meetings | Actively engaging in team brainstorming sessions
2 | Sprint 3 | 2024-11-16 | 2024-11-22 | B.Varshitha Sri | Revisiting basic data structures and algorithms weekly | Procrastinating on debugging known issues | Maintaining focus on coding | Reviewing and optimizing existing code for better performance
3 | Sprint 4 | 2024-11-23 | 2024-11-29 | B.Varshitha Sri | Engaging in online coding challenges for problem-solving | Overcomplicating solutions instead of keeping them simple | Asking for help when stuck. | Staying consistent with daily learning and skill improvement
4 | sprint 5 | 2024-12-02 | 2024-12-06 | B.Varshitha Sri | Collaborating with peers on study groups and assignments | Neglecting to seek feedback on work in progress | Collaborating on language processing strategies & modules for U.I building | Sharing knowledge and resources with peers for mutual growth.